## Tab 1 - Prioritization
# | Action Description | Is there sufficient staff to implement the project? | Is training required for the staff to implement the project? | Is there political support for the project? | Does the community have the legal authority to do the project? | What is the cost of the project? | Does the community have the funds for the project on the whole or the local match? | Does the action advance other local objectives or plans? | What is the scale of the overall benefit? | Will the action adversely affect priority populations? | Does the action build resilience for priority populations? | What priority was this action assigned at the MVP Community Resilience Building Workshops? | Overall Priority | Selected for Implementation? | Is there sufficient staff to implement the project? | Is training required for the staff to implement the project? | Is there political support for the project? | Does the community have the legal authority to do the project? | What is the cost of the project? | Does the community have the funds for the project on the whole or the local match? | Does the action advance other local objectives or plans? | What is the scale of the overall benefit? | Will the action adversely affect priority populations? | Does the action build resilience for priority populations? | What priority was this action assigned at the MVP Community Resilience Building Workshops? | Sum
|  | Yes No | Yes No | Yes No Maybe | Yes No Maybe | $ = <$50,000 $$ = $50,000 to <$250,000 $$$ = $250,000 or more | Yes No Maybe | Yes No | High (regional, town-wide) Medium (neighborhood specific) Low (site specific) | Yes No Maybe | Yes No Maybe | High Medium Low N/A (from 2015 HMP) | High Medium Low | Yes No
1 | Fire Department Station/ Lot Resilience | Yes | No | Maybe | Yes | $$ | No | Yes | Low | No | No | High | Medium | Yes | 3 | 0 | 2 | 3 | 2 | 0 | 3 | 0 | 0 | 0 | 3 | 16 | 15
2 | Road infrastructure evaluation and management plan | Yes | Yes | Yes | Yes | $$ | Maybe | Yes | High | No | Yes | High | High | Yes | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 0 | 3 | 3 | 28 | 27
3 | Woodwards Mill Pond Dam Repairs | Yes | No | Yes | Yes | $$ | Maybe | Yes | Medium | No | No | High | Medium | No | 3 | 0 | 3 | 3 | 2 | 2 | 3 | 2 | 0 | 0 | 3 | 21 | 19
4 | Communication plan for priority populations | Yes | No | Yes | Yes | $ | Yes | No | Medium | No | Yes | High | High | Yes | 3 | 0 | 3 | 3 | 3 | 3 | 0 | 2 | 0 | 3 | 3 | 23 | 22
5 | Create cooling areas (e.g., natural approaches & structures) at Larter Field, Town Common, school parking lot | No | No | No | Yes | $$ | Maybe | No | Medium | No | Yes | High | Low | No | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 2 | 0 | 3 | 3 | 15 | 15
6 | Culverts & Dams: inventory & evaluation and flood study regarding prevention | Yes | Yes | Yes | Maybe | $$ | Maybe | Yes | High | No | No | High | High | Yes | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 3 | 24 | 23
7 | Education & Outreach for Invasives, Wells, Trees, Flooding | Yes | No | Yes | Yes | $ | Yes | No | High | No | Yes | High | High | Yes | 3 | 0 | 3 | 3 | 3 | 3 | 0 | 3 | 0 | 3 | 3 | 24 | 23
8 | Install mixer at water tower | Yes | No | Yes | Yes | $$ | Maybe | Yes | Medium | No | No | High | Medium | No | 3 | 0 | 3 | 3 | 2 | 2 | 3 | 2 | 0 | 0 | 3 | 21 | 20
9 | Complete a review of bylaws & regulations for climate resilience | Yes | No | Yes | Yes | $ | Yes | Yes | High | Maybe | Maybe | High | High | Yes | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 28 | 28
10 | Generators for heating/cooling at critical buildings | Yes | No | Yes | Yes | $$ | Maybe | Maybe | Medium | No | Yes | High | High | Yes | 3 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 3 | 3 | 23 | 22
11 | Develop List of Emergency Shelters in other communities (including Pepperell) | Yes | No | Yes | Yes | $ | Yes | Yes | Medium | No | Yes | High | High | Yes | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 3 | 3 | 26 | 25
12 | Improve and create affordable senior housing options | Yes | No | Yes | Maybe | $$$ | Maybe | Yes | High | No | Yes | High | Medium | No | 3 | 0 | 3 | 2 | 0 | 2 | 3 | 3 | 0 | 3 | 3 | 22 | 20
13 | Improve access roads to open / wooded spaces for fire management and emergency response | Yes | No | Yes | Yes | $$ | Maybe | No | Medium | No | No | High | Medium | Yes | 3 | 0 | 3 | 3 | 2 | 2 | 0 | 2 | 0 | 0 | 3 | 18 | 17
14 | Add AC to school for shelter use/ designation | Yes | No | Yes | Yes | $ | Maybe | Yes | Medium | No | Yes | High | High | Yes | 3 | 0 | 3 | 3 | 3 | 2 | 3 | 2 | 0 | 3 | 3 | 25 | 24
15 | Implement Building Envelop Actions at Union School | Yes | No | Yes | Yes | $$$ | Maybe | Yes | Low | No | No | Medium | Medium | Yes | 3 | 0 | 3 | 3 | 0 | 2 | 3 | 0 | 0 | 0 | 2 | 16 | 15
16 | Mitigate potential impacts of flooding and other natural hazards at new development projects | Yes | No | Maybe | Maybe | $ | Yes | Yes | High | Maybe | Maybe | Medium | High | Yes | 3 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 25 | 23
17 | Flood study for DPW | Yes | Yes | No | Yes | $ | Maybe | Yes | Low | No | No | Medium | Medium | No | 3 | 3 | 0 | 3 | 3 | 2 | 3 | 0 | 0 | 0 | 2 | 19 | 18
18 | Develop policies for use for Library/Council on Aging | Yes | No | Yes | Yes | $ | Yes | Yes | Low | No | Yes | Medium | High | Yes | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 2 | 23 | 22
19 | Provide access to drinking water from town on public properties (e.g., water fountains, fill stations) | No | No | Maybe | Yes | $$ | Maybe | Yes | Low | No | Yes | Low | Low | No | 0 | 0 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 3 | 0 | 15 | 14
20 | Adapt community activities to seasons/weather (time to avoid natural hazards) | Yes | No | Yes | No | $ | Yes | Yes | Medium | No | Yes | Low | Medium | No | 3 | 0 | 3 | 0 | 3 | 3 | 3 | 2 | 0 | 3 | 0 | 20 | 18
21 | Develop procedure and obtain equipment for fire department to pump basements | Yes | No | Maybe | Yes | $ | Maybe | Maybe | Medium | No | Yes | Low | Medium | No | 3 | 0 | 2 | 3 | 3 | 2 | 2 | 2 | 0 | 3 | 0 | 20 | 18
22 | Gas / power / energy resilience study | No | No | No | Maybe | $$ | No | Maybe | High | No | Maybe | Low | Low | No | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 3 | 0 | 2 | 0 | 11 | 10
23 | Regional Coordination for Cow Pond Dam | Yes | No | Maybe | Maybe | $ | Yes | Yes | Medium | No | No | Low | Medium | No | 3 | 0 | 2 | 2 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 18 | 16
24 | Police Department resilience study | No | No | No | Yes | $$ | No | No | Low | No | No | Low | Low | No | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8
25 | Hydrant inventory & code identification | Yes | No | Yes | Yes | $ | maybe | Yes | Medium | No | Maybe | Low | Medium | No | 3 | 0 | 3 | 3 | 3 | 2 | 3 | 2 | 0 | 2 | 0 | 21 | 19
26 | In-person emergency communications plan | Yes | No | Yes | Yes | $ | Yes | Maybe | High | No | Yes | Low | Medium | No | 3 | 0 | 3 | 3 | 3 | 3 | 2 | 3 | 0 | 3 | 0 | 23 | 21
27 | Encourage sign ups for outreach systems, priority populations in particular | Yes | No | Yes | Yes | $ | Yes | Yes | High | No | Yes | Low | High | No | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 0 | 24 | 22
28 | Downtown flooding study | No | Yes | Maybe | Yes | $$ | No | Yes | Medium | No | Maybe | Low | Medium | No | 0 | 3 | 2 | 3 | 2 | 0 | 3 | 2 | 0 | 2 | 0 | 17 | 16
29 | Add cell tower for equal service in case of emergencies | No | No | Maybe | Maybe | $$$ | No | Yes | High | No | Yes | Low | Low | No | 0 | 0 | 2 | 2 | 0 | 0 | 3 | 3 | 0 | 3 | 0 | 13 | 13
30 | Beaver management planning | Yes | No | Maybe | Yes | $ | Yes | Yes | Medium | No | No | Low | Medium | No | 3 | 0 | 2 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 19 | 17
31 | Ongoing maintenance of trees surrounding critical facilities, pre storm event | Yes | No | Yes | Maybe | $ | Yes | Yes | High | No | Maybe | Low | Medium | No | 3 | 0 | 3 | 2 | 3 | 3 | 3 | 3 | 0 | 2 | 0 | 22 | 21
32 | Resilient Bandstand at Town Common | Yes | No | Maybe | Yes | $$$ | No | Maybe | Low | No | Yes | Low | Low | No | 3 | 0 | 2 | 3 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 13 | 13
33 | Splash pad at Larter Field | Yes | No | Maybe | Yes | $$$ | No | Maybe | Low | No | Yes | Low | Low | No | 3 | 0 | 2 | 3 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 13 | 14
34 | Study the Community Rating System to determine appropriateness for Dunstable | Yes | No | Maybe | Yes | $$ | No | Maybe | Medium | No | Yes | N/A | Medium | Yes | 3 | 0 | 2 | 3 | 2 | 0 | 2 | 2 | 0 | 3 | 0 | 17 | 16
35 | Increase public awareness of the dangers of extreme temperatures and outline locations where vulnerable populations (elderly and those with health issues) can have access to air conditioning or shelter from the cold | No | Yes | Maybe | Yes | $$ | Maybe | Yes | Medium | No | Maybe | N/A | Medium | Yes | 0 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 0 | 2 | 0 | 19 | 17
36 | Work with DCR Office of Dam Safety to ensure that the inspections of all dams are current. | Yes | No | Yes | Yes | $ | Yes | Yes | High | Maybe | Maybe | N/A | High | Yes | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 0 | 25 | 24
37 | Incorporate Hazard Mitigation into subdivision regulations, Master Plan, and Open Space Plan updates | Yes | Yes | Yes | Yes | $ | No | Yes | Medium | No | No | N/A | Medium | Yes | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 2 | 0 | 0 | 0 | 20 | 19
38 | Participate in DCR's Fire Wise Program for the forested sections of town | Yes | Yes | Maybe | Yes | $ | Yes | Maybe | Medium | No | No | N/A | Medium | No | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 21 | 20
39 | Ensure that administrators of schools, businesses, and municipal buildings have a shelter plan in the event of a tornado warning | Yes | Yes | Yes | Yes | $ | No | Yes | High | Maybe | Maybe | N/A | High | Yes | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 2 | 2 | 0 | 25 | 24
40 | Study the establishment of a mutual aid agreement with neighboring communities to administer NFIP following a major storm event | Yes | Yes | Yes | Maybe | $ | Yes | Yes | High | No | No | N/A | High | Yes | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 23 | 22
41 | Distribute educational information to residents and businesses on protecting life and property from severe winter storm events | Yes | No | Maybe | Yes | $ | Maybe | Yes | High | No | Yes | N/A | Medium | No | 3 | 0 | 2 | 3 | 3 | 2 | 3 | 3 | 0 | 3 | 0 | 22 | 20
42 | Inspect public buildings to evaluate the capacity to withstand snow loads and prevent roof collapse. Develop plans to clear roofs of excessive snow accumulations to prevent collapse. | No | No | Maybe | Yes | $$ | No | Maybe | Medium | No | Maybe | N/A | Low | No | 0 | 0 | 2 | 3 | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 13 | 13

## Tab 2 - 2024 HMP Actions
Action # | Action Description | Hazards / Risks Addressed | Goals Addressed | Responsible Party | Partner Agencies | Overall Priority | Cost Estimate | Potential Funding Source(s) | Timeframe to Start | Estimated Timeline for Completion | Integration Status | Integration Opportunity
[5 empty] | Can any stakeholders help carry out the action, and if so, who? | High Medium Low | $ = <$50,000 $$ = $50,000 to <$250,000 $$$ = $250,000 or more | Capital Budget Operating Budget Municipal Bond Grant Staff Time | In Progress Less than 1 year 1-2 years 2-5 years Annual | Short-term Medium-term Long-term | Action Identified in other Local Plan? Yes No | Action could support other local plan or planning mechanism? Yes No
1 | Fire Department Station/ Lot Resilience | Precipitation flooding, winter storms | 1. Protect Health and Safety 3. Increase Response Capacity 6. Integrate Climate Change | Fire Dept | Select Board | Medium | $$ | Capital Budget / Municipal Bond | In Progress | Long-term | Yes | No
2 | Road infrastructure evaluation and management plan | Precipitation flooding, | 1. Protect Health and Safety 5. Consider the Economy 6. Integrate Climate Change | Road Commission | Highway Department | High | $$ | Capital Budget / Operating Budget / Grant | In Progress | Short-term | Yes | Yes
3 | Woodwards Mill Pond Dam Repairs | Drought, precipitation flooding | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change | Select Board | Conservation Commsion | Medium | $$ | Capital Budget / Grant | In Progress | Short-term | Yes | Yes
4 | Communication plan for priority populations | All hazards | 1. Protect Health and Safety 3. Increase Response Capacity 4. Protect Priority Populations 6. Integrate Climate Change | Police | Senior Center | High | $ | Staff Time | Less than 1 year | Short-term | No | Yes
5 | Create cooling areas (e.g., natural approaches & structures) at Larter Field, Town Common, school parking lot | Average/Extreme temperatures | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change 10. Be Sustainable | Selecdt Board | Community Preservation Committee | Low | $$ | Grant | 1-2 years | Short-term | No | Yes
6 | Culverts & Dams: inventory & evaluation and flood study regarding prevention | Precipitation flooding | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change | Road Commission | Highway Department | High | $$ | Capital Budget / Grant | In Progress | Medium-term | Yes | Yes
7 | Education & Outreach for Invasives, Wells, Trees, Flooding | Invasive Species, drought, wildfires | 1. Protect Health and Safety 2. Increase Outreach and Education 6. Integrate Climate Change | Town Forest Committee | Conservation Commsion | High | $ | Staff Time / Grant | In Progress | Short-term | No | No
8 | Install mixer at water tower | Drought | 1. Protect Health and Safety 3. Increase Response Capacity 6. Integrate Climate Change | Water Commission | Select Board | Medium | $$ | Capital Budget / Municipal Bond | 1-2 years | Short-term | Yes | Yes
9 | Complete a review of bylaws & regulations for climate resilience | All hazards | 1. Protect Health and Safety 2. Increase Outreach and Education 5. Consider the Economy 6. Integrate Climate Change 7. Encourage Smart Development 8. Be Sustainable | Planning Board | Zoning Board of Appeals / Conservation Commission, Select Board | High | $ | Staff Time / Grant | Less than 1 year | Short-term | Yes | Yes
10 | Generators for heating/cooling at critical buildings | Average/Extreme temperatures | 1. Protect Health and Safety 3. Increase Response Capacity 4. Protect Priority Populations 6. Integrate Climate Change | Emergency Management Director | Police, Fire, Select Board | High | $$ | Municipal Bond / Grant | 1-2 years | Short-term | No | Yes
11 | Develop List of Emergency Shelters in other communities (including Pepperell) | All hazards except changes in groundwater and invasive species | 1. Protect Health and Safety 2. Increase Outreach and Education 4. Protect Priority Populations 6. Integrate Climate Change 8. Increase Coordination | Emergency Management Director | Select Board | High | $ | Staff Time | Less than 1 year | Short-term | No | Yes
12 | Improve and create affordable senior housing options | All hazards except changes in groundwater and invasive species | 4. Protect Priority Populations 6. Integrate Climate Change 7. Encourage Smart Development | Affordable Housing Committee | NMCOG / Affordable Housing Committee | Medium | $$$ | Staff Time / Grant | In Progress | Medium-term | Yes | Yes
13 | Improve access roads to open / wooded spaces for fire management and emergency response | Wildfires | 1. Protect Health and Safety 3. Increase Response Capacity 6. Integrate Climate Change | Town Forest Committee | Road Commission | Medium | $$ | Operating Budget / Grant | In Progress | Short-term | No | Yes
14 | Add AC to school for shelter use/ designation | Average/Extreme temperatures | 1. Protect Health and Safety 3. Increase Response Capacity 4. Protect Priority Populations 6. Integrate Climate Change | Schools | Emergency Management Director | High | $ | Municipal Bond / Grant | 1-2 years | Short-term | No | Yes
15 | Implement Building Envelop Actions at Union School | Average/Extreme temperatures, precipitation flooding, winter storms, hurricanes, tornadoes, earthquakes | 1. Protect Health and Safety 3. Increase Response Capacity 4. Protect Priority Populations 6. Integrate Climate Change | Select Board | CPC, Historical Commission | Medium | $$$ | Capital Budget / Grant | 1-2 years | Short-term | Yes | Yes
16 | Mitigate potential impacts of flooding and other natural hazards at new development projects | Precipitation flooding | 1. Protect Health and Safety 2. Increase Outreach and Education 5. Consider the Economy 6. Integrate Climate Change 7. Encourage Smart Development 8. Be Sustainable | Planning Board | Zoning Board of Appeals / Conservation Commission | High | $ | Staff Time / Grant | Less than 1 year | Short-term | Yes | Yes
17 | Flood study for DPW | Precipitation flooding | 1. Protect Health and Safety 3. Increase Response Capacity 6. Integrate Climate Change | Road Commission | Town Engineer | Medium | $ | Municipal Bond / Grant | 1-2 years | Short-term | No | Yes
18 | Develop policies for use for Library/Council on Aging | All hazards except changes in groundwater and invasive species | 1. Protect Health and Safety 2. Increase Outreach and Education 4. Protect Priority Populations 6. Integrate Climate Change | Library Trustees | Council on Aging | High | $ | Staff Time | Less than 1 year | Short-term | No | No
19 | Provide access to drinking water from town on public properties (e.g., water fountains, fill stations) | Drought, average/extreme temperatures | 1. Protect Health and Safety 2. Increase Outreach and Education 3. Increase Response Capacity 4. Protect Priority Populations 6. Integrate Climate Change | Water Commission | Planning Board, Select Board | Low | $$ | Municipal Bond / Grant | 2-5 years | Long-term | No | Yes
20 | Adapt community activities to seasons/weather (time to avoid natural hazards) | All hazards | 1. Protect Health and Safety 2. Increase Outreach and Education 4. Protect Priority Populations 6. Integrate Climate Change 8. Increase Coordination | Emergency Management Director | Cultural Council | Medium | $ | Staff Time | Less than 1 year | Short-term | No | No
21 | Develop procedure and obtain equipment for fire department to pump basements | Precipitation flooding | 1. Protect Health and Safety 3. Increase Response Capacity 6. Integrate Climate Change | Fire Dept | Emergency Management Director | Medium | $ | Staff Time | In Progress | Short-term | No | No
22 | Gas / power / energy resilience study | All hazards | 1. Protect Health and Safety 3. Increase Response Capacity 5. Consider the Economy 6. Integrate Climate Change 7. Encourage Smart Development 10. Be Sustainable | Emergency Management Director | NMCOG | Low | $$ | Grant | 1-2 years | Long-term | No | No
23 | Regional Coordination for Cow Pond Dam | Precipitation flooding | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change 8. Increase Coordination | Conservation Commisoin | NMCOG | Medium | $ | Staff Time | Less than 1 year | Short-term | No | Yes
24 | Police Department resilience study | All hazards | 1. Protect Health and Safety 3. Increase Response Capacity 6. Integrate Climate Change | Police | Select Board | Low | $$ | Grant | 1-2 years | Medium-term | No | No
25 | Hydrant inventory & code identification | Wildfires | 1. Protect Health and Safety 3. Increase Response Capacity | Fire Dept | Emergency Management Director | Medium | $ | Staff Time | Less than 1 year | Short-term |  | No
26 | In-person emergency communications plan | All hazards | 1. Protect Health and Safety 2. Increase Outreach and Education 6. Integrate Climate Change | Police | Emergency Management Director | Medium | $ | Staff Time | Less than 1 year | Short-term | No | Yes
27 | Encourage sign ups for outreach systems, priority populations in particular | All hazards | 1. Protect Health and Safety 2. Increase Outreach and Education 6. Integrate Climate Change | Select Board | Council on Aging | High | $ | Staff Time | Less than 1 year | Short-term | No | No
28 | Downtown flooding study | Precipitation flooding, hurricanes | 1. Protect Health and Safety 4. Protect Priority Populations 5. Consider the Economy 6. Integrate Climate Change | Road Commission | Select Board, Town Engineer | Medium | $$ | Grant | 1-2 years | Medium-term | No | Yes
29 | Add cell tower for equal service in case of emergencies | All hazards | 1. Protect Health and Safety 3. Increase Response Capacity 8. Increase Coordination | Police, Fire | Select Board | Low | $$$ | Municipal Bond / Grant | 2-5 years | Long-term | No | Yes
30 | Beaver management planning | Precipitation flooding | 1. Protect Health and Safety 6. Integrate Climate Change | Board of Health | Road Commission Conservation Commission | Medium | $ | Operating Budget / Grant | Less than 1 year | Long-term | Yes | Yes
31 | Ongoing maintenance of trees surrounding critical facilities, pre storm event | winter weather, hurricanes | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change 8. Increase Coordination | Road Commission | Town Forest Committee | Medium | $ | Operating Budget / Grant | Annual | Long-term | No | Yes
32 | Resilient Bandstand at Town Common | Average/extreme temperatures | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change | Select Board | Cultural Council | Low | $$$ | Capital Budget / Municipal Bond / Grant | 2-5 years | Medium-term | No | No
33 | Splash pad at Larter Field | Average/extreme temperatures | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change | Emergency Management Director | Water CommissionCommunity Preservation Committee | Low | $$$ | Capital Budget / Municipal Bond / Grant | 2-5 years | Medium-term | No | No
34 | Study the Community Rating System to determine appropriateness for Dunstable | Precipitation flooding | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change | Select Board | NMCOG | Medium | $$ | Staff Time / Grant | 1-2 years | Short-term | No | Yes
35 | Increase public awareness of the dangers of extreme temperatures and outline locations where vulnerable populations (elderly and those with health issues) can have access to air conditioning or shelter from the cold | Average/extreme temperatures | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change | Emergency Management Director | Police, Fire, Select Board | Medium | $$ | Staff Time / Grant | annual | short-medium term | No | Yes
36 | Work with DCR Office of Dam Safety to ensure that the inspections of all dams are current. | Precipitation flooding | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change | Select Board | Road Commission Conservation Commission | High | $ | Staff Time / Grant | 1-2 years | medium term | No | Yes
37 | Incorporate Hazard Mitigation into subdivision regulations, Master Plan, and Open Space Plan updates | All hazards | 1. Protect Health and Safety 2. Increase Outreach and Education 5. Consider the Economy 6. Integrate Climate Change 7. Encourage Smart Development 8. Increase Coordination 10. Be Sustainable | Planning Board | Zoning Board of Appeals / Conservation Commission / Master Plan Committee | Medium | $ | Staff Time | Less than 1 year | Short-term | No | Yes
38 | Participate in DCR's Fire Wise Program for the forested sections of town | Wildfires | 1. Protect Health and Safety 4. Protect Priority Populations 6. Integrate Climate Change | Fire Dept | Town Forest Committee | Medium | $ | Staff Time | Annual | Long-term | No | Yes
39 | Ensure that administrators of schools, businesses, and municipal buildings have a shelter plan in the event of a tornado warning | Tornados | 1. Protect Health and Safety 3. Increase Response Capacity 6. Integrate Climate Change 8. Increase Coordination | Schools | Police / Fire | High | $ | Staff Time / Grant | Annual | Long-term | No | Yes
40 | Study the establishment of a mutual aid agreement with neighboring communities to administer NFIP following a major storm event | All hazards | 1. Protect Health and Safety 3. Increase Response Capacity 6. Integrate Climate Change 8. Increase Coordination | Select Board | NMCOG | High | $ | Staff Time | Annual | Long-term | No | Yes